## PIC Feature Final Project
Sanbercode Batch 5 Final Project Kelompok 5
No | Project Name | Feature List | Kelompok | PIC
1 | Orange HRM | Login & Logout | Kelompok 5 | Indah Azzura
2 |  | Menu Admin - User Management - Users |  | Indah Azzura
3 |  | Menu Admin - User Management - Users - Add User |  | Rizky Melinda Pranati
4 |  | Menu Admin - User Management - Users - Edit User |  | Rizky Melinda Pranati
5 |  | Menu Admin - User Management - Users - Delete User |  | Rizky Melinda Pranati
6 |  | Menu Admin - Organization |  | Agnes Zahrani
7 |  | Menu Admin - Organization - Add Locations |  | Agnes Zahrani
8 |  | Menu Admin - Organization - Edit Locations |  | Agnes Zahrani
9 |  | Menu Admin - Organization - Delete Locations |  | Putri Syahrani
10 |  | Menu PIM - Employee List |  | Putri Syahrani
11 |  | Menu PIM - Add Employee |  | Muhammad Rizky Ansari
12 |  | Menu PIM - Edit Employee |  | Muhammad Rizky Ansari
13 |  | Menu PIM - Delete Employee |  | Muhammad Rizky Ansari

## 3 Melinda Admin - Add User
Project Name | Final Project QA Sanbercode Batch 45 Kelompok 5
Modul Name | Admin-User
Sub Menu | Add User
Testing Environment | -
URL | https://opensource-demo.orangehrmlive.com/
Created By | Rizky Melinda Pranati
Creation Date | 2023-06-02
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Test Category | Test Data | Expected Result | Actual Result | Status | Network Response | Attachment Details | Comments | Executed Date
TS-USER-01 | Testing Menu as an Admin to Add User | TC-AddUser-01 | Testing Login as an Admin | : https://opensource-demo.orangehrmlive.com/web/index.php/auth/login | Positive | Username : Admin ¦ Password : admin123 | Successfully Login as an Admin, and Get into Admin Dashboard | As Expected | PASS |  |  |  | 2023-06-02
2. Login Using Admin Account
3. Input Username
4. Input Password
5. Click Login Button
|  | TC-AddUser-02 | Navigate Admin Menu Testing | 1. Repeat Step TC-AddUser-01 | Positive |  | Navigate to User Management Drop-Down and Click Users: https://opensource-demo.orangehrmlive.com/web/index.php/admin/viewSystemUsers | As Expected | PASS |  |  |  | 2023-06-02
2. Click Admin Button on Left Sidebar Menu
3. Click Users
|  | TC-AddUser-03 | Navigate Add User Function Testing | 1.Repeat Step TC-AddUser-01 | Positive |  | Navigate to Add User Page : https://opensource-demo.orangehrmlive.com/web/index.php/admin/saveSystemUser | As Expected | PASS |  |  |  | 2023-06-02
2.Click Admin Button on Left Sidebar Menu
3.Click Add Users
4. Click Add Button
|  | TC-AddUser-04 | Testing Add New User Data from Employee Data | 1. Repeat Step TC-AddUser-01 | Positive | Firstname* : Rizky | Successfully Add User Data from Data Employee | As Expected | PASS |  |  |  | 2023-06-02
|  |  |  | 2. Click Admin Button on Left Sidebar Menu |  | Last Name* : Ansari
3.Click Add Users
4. Click Add Button
5. Fill Required Field
6. Click Save Button
|  | TC-AddUser-05 | Testing Add New User Data from Employee Data ¦ Case: Using The Same Username | 1. Repeat Step TC-AddUser-01 | Negative | Firstname* : Rizky | Fail Add User with Notification: Already exists | As Expected | PASS |  |  |  | 2023-06-02
|  |  |  | 2. Click Admin Button on Left Sidebar Menu |  | Last Name* : Ansari
|  |  |  | 3.Click Add Users |  | Username: Afc123
4. Click Add Button
5. Fill Required Field
6. Fill Field Username with Exisiting Username
6. Click Save Button
|  | TC-AddUser-06 | Testing Add New User Data ¦ Case: Not Input One or More Required Field | 1. Repeat Step TC-AddUser-01 | Negative |  | Fail Add User with Notification: Required | As Expected | PASS |  |  |  | 2023-06-02
2. Click Admin Button on Left Sidebar Menu
3.Click Add Users
4. Click Add Button
5. Not Input One or More Required Field
6. Click Save Button
|  | TC-AddUser-07 | TestingAdd New User Data ¦ Case: Input Not The Same Password between Password and Confirm Password Field | 1. Repeat Step TC-AddUser-01 | Negative | Password: abc123 | Fail Add User with Notification: Password do not match | As Expected | PASS |  |  |  | 2023-06-02
|  |  |  | 2. Click Admin Button on Left Sidebar Menu |  | Confirm Password: abc456
3.Click Add Users
4. Click Add Button
5. Not Input The Same Password between Password and Confirm Password Field
6. Click Save Button

## 4 Melinda Admin - Edit User
Project Name | Final Project QA Sanbercode Batch 45 Kelompok 5
Modul Name | Admin-User
Sub Menu | Edit User
Testing Environment | -
URL | https://opensource-demo.orangehrmlive.com/
Created By | Rizky Melinda Pranati
Creation Date | 2023-06-02
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Test Category | Test Data | Expected Result | Actual Result | Status | Network Response | Attachment Details | Comments | Executed Date
TS-USER-02 | Testing Menu as an Admin to Edit User | TC-EditUser-01 | Testing Login as an Admin | 1. Go To : https://opensource-demo.orangehrmlive.com/web/index.php/auth/login | Positive | Username : Admin ¦ Password : admin123 | Successfully Login as an Admin, and Get into Admin Dashboard | As Expected | PASS |  |  |  | 2023-06-02
2. Login Using Admin Account
3. Input Username
4. Input Password
5. Click Login Button
|  | TC-EditUser-02 | Navigate Admin Menu Testinga | 1. Repeat Step TC-EditUser-01 | Positive |  | Navigate to User Management Drop-Down and Click Users: https://opensource-demo.orangehrmlive.com/web/index.php/admin/viewSystemUsers | As Expected | PASS |  |  |  | 2023-06-02
2. Click Admin Button on Left Sidebar Menu
3. Click Users
|  | TC-EditUser-03 | Testing Edit Function ¦ Case: Edit Username | 1. Repeat Step TC-EditUser-01 | Positive |  | Successfully Edit Username from Data Employee with Notification: Successfully update | As Expected | PASS |  |  |  | 2023-06-02
|  |  |  | 2. Choose 1 User Data |  | Edit Username: Aaliyahhaq
3. Click Edit Icon
4. Navigate to Detail User Data
5. Edit Username
6. Click Save Button
|  | TC-EditUser-04 | Testing Edit Function ¦ Case: Edit Status | 1. Repeat Step TC-EditUser-01 | Positive | Edit Status: Disable | Successfully Status from Data Employee with Notification: Successfully update | As Expected | PASS |  |  |  | 2023-06-02
2. Choose 1 User Data
3. Click Edit Icon
4. Navigate to Detail User Data
5. Edit Status
6. Click Save Button
|  | TC-EditUser-05 |  | 1. Repeat Step TC-EditUser-01 | Positive | User Role: Admin | Successfully User Role from Data Employee with Notification: Successfully update | As Expected | PASS |  |  |  | 2023-06-02
2. Choose 1 User Data
3. Click Edit Icon
4. Navigate to Detail User Data
5. Edit User Role
|  |  | Testing Edit Function ¦ Case: User Role | 6. Click Save Button
|  | TC-EditUser-06 | Testing Edit Function ¦ Case: Change Unmatch Password | 1. Repeat Step TC-PIMEDT-01 | Negative | Password: qwerty123 | Fail Add User with Notification: Password do not match | As Expected | PASS |  |  |  | 2023-06-02
|  |  |  | 2. Choose 1 User Data |  | Confirm Password: qwerty456
3. Click Edit Icon
4. Navigate to Detail User Data
5. Edit Change Password
6. Click Save Button

## 5 Melinda Admin - Delete User
Project Name | Final Project QA Sanbercode Batch 45 Kelompok 5
Modul Name | Admin-User
Sub Menu | Delete User
Testing Environment | -
URL | https://opensource-demo.orangehrmlive.com/
Created By | Rizky Melinda Pranati
Creation Date | 2023-06-02
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Test Category | Test Data | Expected Result | Actual Result | Status | Network Response | Attachment Details | Comments | Executed Date
TS-USER-03 | Testing Menu as an Admin to Delete User | TC-DeleteUser-01 | Testing Login as an Admin | 1. Go To : https://opensource-demo.orangehrmlive.com/web/index.php/auth/login | Positive | Username : Admin ¦ Password : admin123 | Successfully Login as an Admin, and Get into Admin Dashboard | As Expected | PASS |  |  |  | 2023-06-02
2. Login Using Admin Account
3. Input Username
4. Input Password
5. Click Login Button
|  | TC-DeleteUser-02 | Navigate Admin Menu Testinga | 1. Repeat Step TC-DeleteUser-01 | Positive |  | Navigate to User Management Drop-Down and Click Users: https://opensource-demo.orangehrmlive.com/web/index.php/admin/viewSystemUsers | As Expected | PASS |  |  |  | 2023-06-02
2. Click Admin Button on Left Sidebar Menu
3. Click Users
|  | TC-DeleteUser-03 | Testing Delete Function ¦ Case: Select Single User Data | 1. Repeat Step TC-DeleteUser-01 | Positive |  | Successfully Delete Single User Data with Notification: Successfully update | As Expected | PASS |  |  |  | 2023-06-02
2. Choose 1 User Data
3. Click Delete Icon
4. Show Pop-Up Confirmation
5. Click Button "Yes, Delete"
|  | TC-DeleteUser-04 | Testing Delete Function ¦ Case: Select Some User Data | 1. Repeat Step TC-DeleteUser-01 | Positive |  | Successfully Delete Some User Data with Notification: Successfully update | As Expected | PASS |  |  |  | 2023-06-02
2. Click Some Check Box
3. Click Delete Icon
4. Show Pop-Up Confirmation
5. Click Button "Yes, Delete"
|  | TC-DeleteUser-05 | Testing Delete Function ¦ Case: Select All User Data | 1. Repeat Step TC-DeleteUser-01 | Positive |  | Successfully Delete All User Data with Notification: Successfully update | As Expected | PASS |  |  |  | 2023-06-02
2. Click Username Check Box
3. Click Delete Icon
4. Show Pop-Up Confirmation
5. Click Button "Yes, Delete"

## 9 Putri Syahrani Admin - Delete
No | TEST SCENARIO ID | FEATURE | SUB FEATURE | TEST CATEGORY | PRECONDITION | TEST CASE ID | TEST CASE | TEST CASE DESCRIPTION | STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS | REMARK
1 | TS.ADM.001 | Admin | Organization | Positive | User already open the website | TC.ADM.001.001 | Delete location | To ensure that user can delete location | 1. Login to the website | Username : Admin Password : admin123 | User can login using valid account | User can login using valid account | Pass
[9 empty] | 2. Click menu "Admin" on the left side |  | Menu can be clicked. The page changed show admin page | Menu can be clicked. The page changed show admin page | Pass
[9 empty] | 3. Click menu "Organication" |  | Menu can be cllicked show more option | Menu can be cllicked show more option | Pass
[9 empty] | 4. Select option "Location" |  | option can be clicked. the page changed show list location | option can be clicked. the page changed show list location | Pass
[9 empty] | 5. Select location you want to delete. Click icon trash |  | Icon can be clicked. Pop up dialog appear. | Icon can be clicked. Pop up dialog appear. | Pass
[9 empty] | 6. Click button "Yes, Delete" |  | User can click the button. Pop notification success. user can delete location | User can click the button. Pop notification success. user can delete location | Pass
2 | TS.ADM.001 | Admin | Organization | Positive | User already open the website | TC.ADM.001.002 | Delete location | To ensure that user can delete selected locations | 1. Login to the website | Username : Admin Password : admin123 | User can login using valid account | User can login using valid account | Pass
[9 empty] | 2. Click menu "Admin" on the left side |  | Menu can be clicked. The page changed show admin page | Menu can be clicked. The page changed show admin page | Pass
[9 empty] | 3. Click menu "Organication" |  | Menu can be cllicked show more option | Menu can be cllicked show more option | Pass
[9 empty] | 4. Select option "Location" |  | option can be clicked. the page changed show list location | option can be clicked. the page changed show list location | Pass
[9 empty] | 5. Checklist locations you want to delete |  | User can select locations they want to delete | User can select locations they want to delete | Pass
[9 empty] | 6. Click button "Delete Selected" |  | button can be clicked. Pop up dialog appear. | button can be clicked. Pop up dialog appear. | Pass
[9 empty] | 7. Click button "Yes, Delete" |  | User can click the button. Pop notification success. user can delete location | User can click the button. Pop notification success. user can delete location | Pass
3 | TS.ADM.001 | Admin | Organization | Positive | User already open the website | TC.ADM.001.003 | Delete location | To ensure that user can delete all locations | 1. Login to the website | Username : Admin Password : admin123 | User can login using valid account | User can login using valid account | Pass
[9 empty] | 2. Click menu "Admin" on the left side |  | Menu can be clicked. The page changed show admin page | Menu can be clicked. The page changed show admin page | Pass
[9 empty] | 3. Click menu "Organication" |  | Menu can be cllicked show more option | Menu can be cllicked show more option | Pass
[9 empty] | 4. Select option "Location" |  | option can be clicked. the page changed show list location | option can be clicked. the page changed show list location | Pass
[9 empty] | 5. Click box checklist beside colomb "Name" |  | User can click the checklist. all locations automatically being checklist | User can click the checklist. all locations automatically being checklist | Pass
[9 empty] | 6. Click button "Delete Selected" |  | button can be clicked. Pop up dialog appear. | button can be clicked. Pop up dialog appear. | Pass
[9 empty] | 7. Click button "Yes, Delete" |  | User can click the button. Pop notification success. user can delete location | User can click the button. Pop notification success. user can delete location | Pass

## 10 Putri Syahrani PIM - Employe
No | TEST SCENARIO ID | FEATURE | SUB FEATURE | TEST CATEGORY | PRECONDITION | TEST CASE ID | TEST CASE | TEST CASE DESCRIPTION | STEPS | TEST DATA | EXPECTED RESULT | ACTUAL RESULT | STATUS | REMARK
1 | TS.PIM.001 | PIM | Employee list | Positive | User already open the website | TC.PIM.001.001 | Detail employee | To ensure that user can view detail employee | 1. Login to the website | Username : Admin Password : admin123 | User can login using valid account | User can login using valid account | Pass
[9 empty] | 2. Click menu "PIM" on the left side |  | Menu can be clicked. The page changed show employee list page | Menu can be clicked. The page changed show employee list page | Pass
[9 empty] | 3. Scroll the page, you can find employee list |  | User can found list employee | User can found list employee | Pass
[9 empty] | 4. Select employee you want to view |  | User can select employee. The page changed shoe detail employee | User can select employee. The page changed shoe detail employee | Pass
2 | TS.PIM.001 | PIM | Employee list | Positive | User already open the website | TC.PIM.001.002 | Search employee | To ensure that user can search for employee | 1. Login to the website | Username : Admin Password : admin123 | User can login using valid account | User can login using valid account | Pass
[9 empty] | 2. Click menu "PIM" on the left side |  | Menu can be clicked. The page changed show employee list page | Menu can be clicked. The page changed show employee list page | Pass
[9 empty] | 3. Fill all fields on employee information |  | The fields can be typed/choosen | The fields can be typed/choosen | Pass
[9 empty] | 4. Click button "Search |  | Button can be clicked. The page changes show search/filter result | Button can be clicked. The page changes show search/filter result | Pass
3 | TS.PIM.001 | PIM | Employee list | Negative | User already open the website | TC.PIM.001.003 | Search employee | To ensure that user can search employee using random format | 1. Login to the website | Username : Admin Password : admin123 | User can login using valid account | User can login using valid account | Pass
[9 empty] | 2. Click menu "PIM" on the left side |  | Menu can be clicked. The page changed show employee list page | Menu can be clicked. The page changed show employee list page | Pass
[9 empty] | 3. Type employee name | example name : wabdkwo | The fields can be typed | The fields can be typed | Pass
[9 empty] | 4. Click button "Search |  | Button can be clicked. The page changes show search/filter result. Notification result appear | Button can be clicked. The page changes show search/filter result. Notification result appear | Pass

## 11 RIZKY PIM - Add Employee
Project Name | Final Project Sanbercode Batch 45 Kelompok 5
Modul Name | PIM
Sub Menu | Add Employee
Testing Environment | -
URL | https://opensource-demo.orangehrmlive.com/
Created By | Muhammad Rizky Ansari
Creation Date | 2023-06-01
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Test Category | Test Data | Expected Result | Actual Result | Status | Network Response | Attachment Details | Comments | Executed Date
TS-PIM-01 | Test PIM Add Employee | TC-PIMADD-01 | Test Login Sebagai Admin | 1. Go To : https://opensource-demo.orangehrmlive.com/web/index.php/auth/login | Positive | Username : Admin ¦ Password : admin123 | Berhasil Login Sebagia Admin & Masuk Ke Dashboard Admin | As Expected | PASS |  |  |  | 2023-06-01
2. Login Menggunakan Akun Admin
3. Input Username
4. Input Password
5. Klick Button Login
|  | TC-PIMADD-02 | Test Nagivasi Menu PIM | 1. Repeat Step TC-PIMADD-01 | Positive |  | Navigate to Page List Employee : https://opensource-demo.orangehrmlive.com/web/index.php/pim/viewEmployeeList | As Expected | PASS |  |  |  | 2023-06-01
2. Klick Button PIM Pada Left Sidebar Menu
|  | TC-PIMADD-03 | Test Navigasi Add Employee | 1. Repeat Step TC-PIMADD-01 | Positive |  | Navigate to Page Add Employee : https://opensource-demo.orangehrmlive.com/web/index.php/pim/addEmployee | As Expected | PASS |  |  |  | 2023-06-01
2. Klick Button PIM Pada Left Sidebar Menu
3. Klick Button Add Employee
|  | TC-PIMADD-04 | Test Add New Data Employee | 1. Repeat Step TC-PIMADD-01 | Positive | Firstname* : Rizky | Berhasil Menambahkan Data Employee | As Expected | PASS |  |  |  | 2023-06-01
|  |  |  | 2. Klick Button PIM Pada Left Sidebar Menu |  | Last Name* : Ansari
3. Klick Button Add Employee
4. Navigate to Page Add Employee
5. Fill Required Field
6. Klick Button Save
|  | TC-PIMADD-05 | Test Add New Data Employee : Case ¦ Using The Same Employee ID | 1. Repeat Step TC-PIMADD-01 | Negative | Firstname* : Rizky | Fail Add Employee With Notif : Employee Id already exists | As Expected | PASS |  |  |  | 2023-06-01
|  |  |  | 2. Klick Button PIM Pada Left Sidebar Menu |  | Last Name* : Ansari
|  |  |  | 3. Klick Button Add Employee |  | Employee Id : 0248
4. Navigate to Page Add Employee
5. Fill Required Field
6. Fill Field ID With Exisiting Employee ID
7. Klick Button Save
|  | TC-PIMADD-06 | Test Add New Data Employee : Case ¦ Null Input First Name | 1. Repeat Step TC-PIMADD-01 | Negative | Firstname* : | Fail Add Employee With Notif : First Name Field Required | As Expected | PASS |  |  |  | 2023-06-01
|  |  |  | 2. Klick Button PIM Pada Left Sidebar Menu |  | Last Name* : Ansari
3. Klick Button Add Employee
4. Navigate to Page Add Employee
5. Null Input Field Firstname
6. Klick Button Save
|  | TC-PIMADD-07 | Test Add New Data Employee : Case ¦ Null Input Last Name | 1. Repeat Step TC-PIMADD-01 | Negative | Firstname* : Rizky | Fail Add Employee With Notif : Last Name Field Required | As Expected | PASS |  |  |  | 2023-06-01
|  |  |  | 2. Klick Button PIM Pada Left Sidebar Menu |  | Last Name* :
3. Klick Button Add Employee
4. Navigate to Page Add Employee
5. Null Input Field Firstname
6. Klick Button Save

## 12 RIZKY PIM - Edit Employee
Project Name | Final Project Sanbercode Batch 45 Kelompok 5
Modul Name | PIM
Sub Menu | Edit
Testing Environment | -
URL | https://opensource-demo.orangehrmlive.com/
Created By | Muhammad Rizky Ansari
Creation Date | 2023-06-01
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Test Category | Test Data | Expected Result | Actual Result | Status | Network Response | Attachment Details | Comments | Executed Date
TS-PIMEDT-01 | Test PIM Edit Data Employee ¦ Personal Details | TC-PIMEDT-01 | Test Login Sebagai Admin | 1. Go To : https://opensource-demo.orangehrmlive.com/web/index.php/auth/login | Positive | Username : Admin ¦ Password : admin123 | Berhasil Login Sebagia Admin & Masuk Ke Dashboard Admin | As Expected | PASS |  |  |  | 2023-06-01
2. Login Menggunakan Akun Admin
3. Input Username
4. Input Password
5. Klick Button Login
|  | TC-PIMEDT-02 | Test Navigation Edit Employee | 1. Repeat Step TC-PIMEDT-01 | Positive |  | Navigate to Selected Detail Employee : https://opensource-demo.orangehrmlive.com/web/index.php/pim/viewPersonalDetails/empNumber/44 | As Expected | PASS |  |  |  | 2023-06-01
2. Pilih 1 Data Employee
3. Click Button Edit
4. Navigate to Detail Employee
|  | TC-PIMEDT-03 | Test Edit : CASE ¦ Edit Personal Details | 1. Repeat Step TC-PIMEDT-01 | Positive | Edit First Name : Chocki | Berhasil Update Data Employee ¦ Show Notification : Successfully Updated | As Expected | PASS |  |  |  | 2023-06-01
|  |  |  | 2. Pilih 1 Data Employee |  | Edit Last Name : Michael
3. Click Button Edit
4. Navigate to Detail Employee
5. Edit Field Personal Details
6. Klick Button Save
|  | TC-PIMEDT-04 | Test Edit Personal Details : CASE ¦ Null Update First Name | 1. Repeat Step TC-PIMEDT-01 | Negative | Edit First Name : | Fail Update Data Employee : Field First Name Notification Required | As Expected | PASS |  |  |  | 2023-06-01
2. Pilih 1 Data Employee
3. Click Button Edit
4. Navigate to Detail Employee
5. Edit Field Personal Details
6. Klick Button Save
|  | TC-PIMEDT-05 | Test Edit Personal Details : CASE ¦ Null Update Last Name | 1. Repeat Step TC-PIMEDT-01 | Negative | Edit Last Name : | Fail Update Data Employee : Field Last Name Notification Required | As Expected | PASS |  |  |  | 2023-06-01
2. Pilih 1 Data Employee
3. Click Button Edit
4. Navigate to Detail Employee
5. Edit Field Personal Details
6. Klick Button Save
|  | TC-PIMEDT-05 | Test Edit Personal Details : CASE ¦ Update With Exisiting Other Employee ID | 1. Repeat Step TC-PIMEDT-01 | Negative | Edit Employee ID : 0070 | Fail Update Data Employee : Field Employee ID Notification Employee Id already exists | Can Change to Existing Other User Employee ID | FAILED |  |  |  | 2023-06-01
2. Pilih 1 Data Employee
3. Click Button Edit
4. Navigate to Detail Employee
5. Edit Field Personal Details
6. Klick Button Save

## 13 RIZKY PIM - Delete Employee
Project Name | Final Project Sanbercode Batch 45 Kelompok 5
Modul Name | PIM
Sub Menu | Delete
Testing Environment | -
URL | https://opensource-demo.orangehrmlive.com/
Created By | Muhammad Rizky Ansari
Creation Date | 2023-06-01
Test Scenario ID | Test Scenario Description | Test Case ID | Test Case Description | Test Steps | Test Category | Test Data | Expected Result | Actual Result | Status | Network Response | Attachment Details | Comments | Executed Date
TS-PIMDEL-01 | Test PIM Delete Data Employee | TC-PIMDEL-01 | Test Login Sebagai Admin | 1. Go To : https://opensource-demo.orangehrmlive.com/web/index.php/auth/login | Positive | Username : Admin ¦ Password : admin123 | Berhasil Login Sebagia Admin & Masuk Ke Dashboard Admin | As Expected | PASS |  |  |  | 2023-06-01
2. Login Menggunakan Akun Admin
3. Input Username
4. Input Password
5. Klick Button Login
|  | TC-PIMDEL-02 | Test Delete : CASE ¦ Select Single Data Employee | 1. Repeat Step TC-PIMDEL-01 | Positive |  | Berhasil Hapus Data Employee ¦ Show Notification : Successfully Deleted | As Expected | PASS |  |  |  | 2023-06-01
2. Pilih 1 Data Employee
3. Click Button Delete Selected
4. Show Pop-Up Confirmation
5. Klick Button "Yes, Delete"
|  | TC-PIMDEL-03 | Test Delete : CASE ¦ Multi Select Data Employee | 1. Repeat Step TC-PIMDEL-01 | Positive |  | Berhasil Hapus Data Employee ¦ Show Notification : Successfully Deleted | As Expected | PASS |  |  |  | 2023-06-01
2. Pilih Lebih dari 1 Data Employee
3. Click Button Delete Selected
4. Show Pop-Up Confirmation
5. Klick Button "Yes, Delete"
|  | TC-PIMDEL-04 | Test Delete : CASE ¦ Select All List Data Employee | 1. Repeat Step TC-PIMDEL-01 | Positive |  | Berhasil Hapus Semua Data Employee ¦ Show Notification : Successfully Deleted | As Expected | PASS |  |  |  | 2023-06-01
2. Klick Check Box ID Pada Data Employee
3. Click Button Delete Selected
4. Show Pop-Up Confirmation
5. Klick Button "Yes, Delete"
|  | TC-PIMDEL-05 | Test Delete : CASE ¦ Direct Delect Using Delete Button | 1. Repeat Step TC-PIMDEL-01 | Positive |  | Berhasil Hapus Data Employee ¦ Show Notification : Successfully Deleted | As Expected | PASS |  |  |  | 2023-06-01
2. Pilih 1 Data Employee
3. Click Button Delete
4. Show Pop-Up Confirmation
5. Klick Button "Yes, Delete"